## Table A Discounted total fund
Category of total discounted cost by funding source | £m
LUF Funding | 15.92
Other Public Sector Funding | 1.86
Private Sector Funding
Total | 17.78
Assumptions
Costs deflated to consistent 2010 price year
Optimism Bias uplift applied at an average 9.3% (3% or 15%, depending on scheme type) and included in discounted costs (see Scheme Costs tab in accompanying economic appraisal spreadsheet)

## Table B Discounted Benefit
Catergory of benefit | £m
Noise | 9228.6101
Local Air Quality | 680987.4484
Greenhouse Gases | 1921646.2385
Journey Quality | 1606960.9316
Physical Activity | 13794481.5531
Accidents | 138429.1522
Economic Efficiency: Consumer Users (Commuting) | 817665.5822
Economic Efficiency: Consumer Users (Other)
Economic Efficiency: Business Users and Providers | 2495859.8711
Wider Public Finances (Indirect Taxation Revenues + NCC financial savings) | 15147853.4583
Total | 36613112.8456
Assumptions
All benefits deflated to 2010 price year
Future benefits (after scheme opening year) discounted at 3.5% per annum.

## Table C Funding Profile
Funding Sources | 2021-22 | 2022-23 | 2023-24 | 2024-25 | Total
UKG Funding Sought | 3.75 | 10.5 | 3.75 |  | 18
Local Authority Contribution | 0.5 | 1 | 0.5 |  | 2
Third Party Contribution |  |  |  |  | 0
Total | 4.25 | 11.5 | 4.25 | 0 | 20

## Table D Costing estimates
Cost heading | Costs (£) | Date Estimated | Status
Streets for People | 10.5m | 2021-06-17 | live
School Streets | 1.5m | 2021-06-17 | live
Greener streets | £8m | 2021-06-17 | live

## Table E Delivery Milestones
Dates
Works Activity | Estimated Date | Opening Date | Completion of works (if different)
Funding awarded | Q3 2021/22 | N/A | N/A
Ward Allocation determined | Q3 2021/22 | N/A | N/A
Measures delivered | Q4 2021/22 | Q4 2021/22 | N/A
Street Lighting Upgrade | Q1 2022/23 | Q1 2022/23 | N/A
EV charge points | Q3 2022/23 | Q3 2022/23 | N/A

## Table F Bid Monitoring and Eval
Ref | Performance Indicators | Data source | Summary of data collection methodology | Indicator for:
|  |  |  | Key Outcome | Mechanism | Objective
/Impact
I_1 | Perception of active travel environment, Perception of Road Safety | Stakeholder surveys: Cyclists | Post implementation surveys delivered by a combination of direct interview, hand out questionnaires and e-survey. | A, B, C, F | M1, M1a, M2, M5, M6, M7, M8, M9, M10, M15, M24, M25 | O1,
Trip Details
Change in behaviour due to new facilities – Mode Switch
Perceptions of accessibility to employment and services
I_2 | Perception of active travel environment, Perception of Road Safety | Stakeholder surveys: Pedestrian | Post implementation surveys delivered by a combination of direct interview, hand out questionnaires and e-survey. | A, B, C, F | M1, M1a, M2, M6, M7, M8, M9, M10, M15, M24, M25 | O1
Trip Details
Change in behaviour due to new facilities – Mode Switch
Perceptions of accessibility to employment and services
I_3 | Perceptions of improved residential environ ment, Perception of active travel environment, Perception of Road Safety | Stakeholder surveys: Residents | Post implementation surveys delivered by a combination of direct interview, hand out questionnaires and e-survey. | A, B, C, F | M1, M1a, M2, M5, M6, M7, M8, M9, M10, M15, M15a, M16 M24, M25 | O1
Trip Details
Change in behaviour due to new facilities – Mode Switch
Perceptions of accessibility to employment and services
I_4 | Frequency, and duration of use, change of charging behaviour | Stakeholder surveys: Charge Point Users | Data from provider | E | M26, M27 | O4
I_5 | Employment and unemployment data | Office for National Statistics | Monthly data published by Department of Work and Pensions | G | M17 | O5
I_6 | Average journey time/delay per vehicle mile | Inrix/C Track data from DfT | Calculated from Inrix/C Track GPS data supplied by the DfT and by data calculated from ANPR data and Google maps | D | M20, M21, M23 | O3
I_7 | Journey time reliability | Inrix/C Track data from DfT |  | D | M20, M21, M23 | O3
I_8 | Modelled changes in NO2, PM2.5 and CO2 emissions | NCC Transport Strategy | Emissions savings due to the RLS interventions will be calculated based on readings from 5 real time air quality analysers, observed mode switch from the stakeholder surveys, traffic flow and composition and mode share surveys at key locations around Derby and Nottingham. | E | M22 | O4
I_9 | Number and % of ULEVs registered in the Derby-Nottingham travel to work area | Office for National Statistics | Quarterly data published by DfT | E | M27 | O4
I_10 | Mode share of travel across cordons in Derby and Nottingham | NCC Highway Metrics team | Annual manual count surveys of people movements across defined cordons in Derby and Nottingham by mode of travel | C | M9 | O2, O3
I_11 | Bespoke before and after mode share surveys in areas benefitting from RLS interventions and comparators | NCC Highway Metrics team | Manual count surveys of people movements across defined cordons by mode of travel. | C | M9 | O2, O3
I_12 | Before and after cycle and pedestrian counts around the locations relevant to the Renewal of Local Streets Programme | NCC Highway Metrics team | Manual and automatic counts of cyclists and pedestrians at council monitoring sites | B | M5, M6, M7, M8, M10, M24, M25 | O2
I_13 | Before and after traffic flows in locations relevant to the Renewal of Local Streets Programme | NCC Highway Metrics team | Manual and automatic counts of traffic at council monitoring sites | C | M3, M12 | O3
I_14 | GVA by local authority area, | Office for National Statistics | Annual data published by ONS | G | M19 | O5
I_15 | Productivity metrics by local authority area | Office for National Statistics | Annual data published by ONS, analysed by council Economic Research officer | G | M14, M18 | O5
I_16 | Estimate of car trips saved, based on observed mode switch | NCC Highway Metrics team | Analysis of mode share and stakeholder user surveys to calculate change | C | M12, M13 | O3
I_17 | Before and after accident and casualty rates among pedestrians and cyclists | NCC and DCC Road Safety teams | Standard data from Police records | A | M3, M4,M5 | Not a direct measure of an objective
I_18 | EV charge point usage measures | Chargemaster | This data is supplied by chargemaster, the provider of EV charge points in Nottingham | E | M26 | Not a direct measure of an objective
I_19 | Power Drawn By Street Lighting on Streets Subject to Greener Streets Theme | Energy Provider | Data from Energy Provider | E | M11 | O4
I_20 | Output Measure | NCC Project Manager | Process Evaluation data from project management records | A | None | O1