## Sheet1
Levelling up Fund Delivery Programme
2021-06-01
|  | amj | jas | ond | jfm | amj | jas | ond | jfm | amj | jas | ond | jfm
|  | 2021/22 |  |  |  | 2022/23 |  |  |  | 2023/24
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Business Case and Approvals | Business case submitted | bar: 2021/22 Q1
Funding Awarded | bar: 2021/22 Q3
Executive board approval to spend | bar: 2021/22 Q3
Streets for people | Ward allocations determined | bar: 2021/22 Q3
Initial design | bar: 2021/22 Q4
Measures delivered | bar: 2021/22 Q4 to 2022/23 Q3
School Streets | Initial Consultation with schools | bar: 2021/22 Q3
Design | bar: 2021/22 Q4
wider consultation will all stakeholders | bar: 2021/22 Q4
implement schemes | bar: 2021/22 Q4 to 2023/24 Q1
Greener Streets | Lighting contract variation agreed | bar: 2021/22 Q3 to 2021/22 Q4
LED replacement programme drawn up | bar: 2022/23 Q1 to 2022/23 Q2
implement LED implementation programme | bar: 2022/23 Q3 to 2023/24 Q4
Meeting with BP chargemaster | bar: 2021/22 Q4
Develop Installation programme | bar: 2022/23 Q1 to 2022/23 Q3
implement installation programme | bar: 2022/23 Q4 to 2023/24 Q4
Comms | Awareness raising (events) | bar: 2021/22 Q4; 2023/24 Q4
Monitoring | bar: 2023/24 Q1 to 2023/24 Q4